## Source
Risk Category | Likelihood, Impact | Control Effectiveness | Mitigation Status | Status | Dept
Operational | 1 | Effective | Planned | Open | Procurement
Financial | 2 | Needs Improvement | In Progress | Monitoring | Finance
Strategic | 3 | Ineffective |  | Mitigated | IT
Compliance | 4 |  |  | Closed | Legal
Reputational | 5 |  |  |  | Management
IT
Governance

## Risk Assessment Matrix
Risk ID | Department | Process / Activity | Risk Title | Risk Description | Risk Category | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Level | Risk Drivers / Root Cause | Potential Business Consequences | Existing Controls | Control Effectiveness | Mitigation Actions | Mitigation Status | Action Owner | Target Completion Date | Status | Residual Likelihood | Residual Impact | Residual Risk Score
R-01 | Procurement | Vendor Selection | PO tanpa kontrak | PO diterbitkan tanpa kontrak tertulis | Compliance | 4 | 5 | 20 | Critical | Tidak ada checklist kontrak | Risiko hukum & sengketa vendor | Review manual oleh staf | Ineffective | Standarisasi kontrak & approval legal | In Progress | Head of Procurement | 2026-01-15 | Monitoring | 2 | 4 | 8
R-02 | Procurement | Vendor Onboarding | Vendor tidak diverifikasi | Vendor belum melalui due diligence | Compliance | 4 | 4 | 16 | Critical | SOP vendor tidak lengkap | Risiko reputasi & fraud | Approval informal | Needs Improvement | Implementasi vendor verification checklist | In Progress | Procurement Manager | 2026-01-10 | Monitoring | 2 | 3 | 6
R-03 | Procurement | Purchasing | Ketergantungan vendor tunggal | Satu vendor dominan tanpa alternatif | Strategic | 3 | 4 | 12 | High | Tidak ada vendor diversification plan | Risiko gangguan supply | Evaluasi tahunan vendor | Needs Improvement | Tambah vendor alternatif | Planned | Supply Chain Lead | 2026-01-31 | Open | 2 | 3 | 6
R-04 | Procurement | Invoice Purchasing | Keterlambatan invoice | Invoice diproses >30 hari | Operational | 3 | 3 | 9 | Medium | Proses manual & backlog | Penalti & gangguan cashflow | Reminder email | Needs Improvement | SLA invoice & monitoring dashboard | Planned | Finance Manager | 2026-02-28 | Open | 2 | 2 | 4
R-05 | Finance | Documentation | Dokumen PO tidak lengkap | Dokumen pendukung tidak konsisten | Operational | 3 | 3 | 9 | Medium | Tidak ada template baku | Audit finding berulang | Review supervisor | Needs Improvement | Template PO & training staf | Planned | Procurement Supervisor | 2026-01-31 | Open | 2 | 2 | 4
R-06 | Legal | Contract Management | Kontrak kadaluarsa | Kontrak tidak dimonitor masa berlaku | Compliance | 3 | 4 | 12 | High | Tidak ada kontrak register | Risiko non-compliance | Arsip manual | Ineffective | Contract register & reminder otomatis | Planned | Legal Head | 2026-01-31 | Open | 2 | 3 | 6
R-07 | IT | System Acccess | Akses sistem bersama | Akun digunakan lebih dari satu user | IT | 3 | 4 | 12 | High | Kontrol akses lemah | Risiko manipulasi data | Password sharing policy | Ineffective | Akun individual & role-based access | Planned | IT Manager | 2026-02-28 | Mitigated | 1 | 3 | 3
R-08 | Procurement | Approval Process | Konflik kepentingan | Approval tanpa deklarasi COI | Reputational | 2 | 4 | 8 | Medium | Tidak ada deklarasi COI | Risiko reputasi & fraud | Etika kerja informal | Needs Improvement | Form deklarasi COI | Planned | Compliance Officer | 2026-01-31 | Open | 1 | 3 | 3
R-09 | Management | Oversight | Monitoring lemah | Tidak ada follow-up rekomendasi audit | Governance | 3 | 4 | 12 | High | Tidak ada tracker resmi | Temuan berulang | Laporan manual | Ineffective | Audit follow-up log terpusat | In Progress | Internal Audit | 2026-02-15 | Monitoring | 2 | 3 | 6
R-10 | Procurement | Reporting | Data procurement tidak akurat | Data PO & invoice tidak sinkron | Operational | 2 | 3 | 6 | Medium | Sistem tidak terintegrasi | Salah keputusan manajemen | Rekonsiliasi manual | Needs Improvement | Rekonsiliasi rutin & dashboard | Planned | Procurement Analyst | 2026-02-28 | Open | 1 | 2 | 2

## Risk Summary
Risk Summary
Low | 0
Medium | 4
High | 4
Critical | 2